## Audit Findings
FindingID | AuditName | AuditDate | Category | Finding | Severity | Recommendation | ResponsibleOfficer | TargetDate | Status | ManagementResponse
AF-001 | Q1 IT Security Audit | 2026-01-31 | Access Management | 15 dormant accounts with active privileges identified in Azure AD | High | Implement automated account deprovisioning after 60 days of inactivity | Identity Manager | 2026-03-31 | Remediated | Automated lifecycle policy configured in Azure AD
AF-002 | Q1 IT Security Audit | 2026-01-31 | Patch Management | 23% of endpoints running OS patches more than 30 days behind | Medium | Reduce patch deployment window to 14 days for critical and 30 days for standard | IT Operations Manager | 2026-04-30 | In Progress | New patch management tool being deployed
AF-003 | Q1 IT Security Audit | 2026-01-31 | Logging | Insufficient log retention — security logs retained for only 30 days | High | Extend log retention to 12 months for security events and 90 days for operational | CISO | 2026-03-31 | Remediated | Log Analytics workspace retention updated
AF-004 | Q1 IT Security Audit | 2026-01-31 | Encryption | Three internal applications transmitting data over HTTP | Critical | Enforce HTTPS for all internal and external application communications | Application Security Lead | 2026-02-28 | Remediated | SSL certificates deployed and HTTP redirects configured
AF-005 | Annual Privacy Audit | 2026-02-28 | Data Retention | No automated enforcement of data retention periods | Medium | Implement automated data lifecycle management aligned with retention schedule | Data Protection Officer | 2026-06-30 | In Progress | DWx Data Lifecycle module being configured
AF-006 | Annual Privacy Audit | 2026-02-28 | Consent Management | Cookie consent banners not capturing granular preferences | Low | Update consent management platform to support category-level consent | Web Development Lead | 2026-05-31 | Open | Vendor evaluation for updated CMP in progress
AF-007 | Annual Privacy Audit | 2026-02-28 | Privacy Notices | Two subsidiary privacy notices not updated for current year | Low | Establish annual privacy notice review cycle with legal review | Privacy Lead | 2026-04-30 | Remediated | Notices updated and review calendar created
AF-008 | SOX Compliance Review | 2026-03-15 | Financial Controls | Manual journal entry approval process lacks segregation of duties | High | Implement dual-approval workflow in ERP for journal entries above $10K | Financial Controller | 2026-06-30 | In Progress | ERP workflow enhancement scoped and approved
AF-009 | SOX Compliance Review | 2026-03-15 | Change Management | IT change management process missing post-implementation reviews | Medium | Add mandatory PIR step to change management workflow for all significant changes | Change Manager | 2026-05-31 | Open | Process update drafted for approval
AF-010 | Vendor Security Audit | 2026-03-31 | Third Party Risk | 2 critical vendors without current security assessments | High | Complete security assessments for all critical and high-risk vendors | Procurement Manager | 2026-04-30 | In Progress | Assessment questionnaires sent to both vendors