## Risk Register
RiskID | Category | RiskDescription | Likelihood | Impact | RiskScore | MitigationStrategy | RiskOwner | Status | LastReviewDate | NextReviewDate
RSK-001 | Cybersecurity | Ransomware attack on production systems | 4 | 5 | 20 | Multi-layered endpoint protection with EDR and weekly backup verification | CISO | Active | 2026-01-15 | 2026-04-15
RSK-002 | Cybersecurity | Phishing attack leading to credential theft | 5 | 4 | 20 | Mandatory quarterly phishing simulations and MFA on all accounts | IT Security Manager | Active | 2026-02-01 | 2026-05-01
RSK-003 | Data Privacy | Unauthorised access to customer PII | 3 | 5 | 15 | Role-based access control with quarterly access reviews and DLP policies | Data Protection Officer | Active | 2026-01-20 | 2026-04-20
RSK-004 | Compliance | Failure to meet GDPR data subject access requests within 30 days | 3 | 4 | 12 | Automated DSAR workflow with SLA tracking in DWx Policy Manager | Privacy Lead | Active | 2026-03-01 | 2026-06-01
RSK-005 | Operational | Key person dependency in infrastructure team | 4 | 3 | 12 | Cross-training programme and documented runbooks for all critical processes | Head of Infrastructure | Mitigating | 2026-02-15 | 2026-05-15
RSK-006 | Financial | Budget overrun on digital transformation programme | 3 | 4 | 12 | Monthly budget reviews with 10% contingency reserve and stage-gate approvals | CFO | Active | 2026-01-10 | 2026-04-10
RSK-007 | Reputational | Data breach resulting in negative media coverage | 2 | 5 | 10 | Incident response plan with pre-approved media statements and PR agency on retainer | Head of Communications | Active | 2026-03-15 | 2026-06-15
RSK-008 | Vendor | Critical SaaS vendor service outage | 3 | 3 | 9 | Multi-vendor strategy for critical services with contractual SLA penalties | Procurement Manager | Active | 2026-02-20 | 2026-05-20
RSK-009 | Legal | Non-compliance with new employment legislation | 2 | 4 | 8 | Legal counsel review of policy updates quarterly with HR compliance tracking | General Counsel | Active | 2026-01-25 | 2026-04-25
RSK-010 | Environmental | Office flood or natural disaster impacting operations | 2 | 4 | 8 | Business continuity plan with remote work capability and off-site backup data centre | Facilities Manager | Active | 2026-03-10 | 2026-06-10
RSK-011 | Cybersecurity | Supply chain compromise via third-party software | 3 | 4 | 12 | Vendor security assessments and software composition analysis for all dependencies | IT Security Manager | Active | 2026-02-10 | 2026-05-10
RSK-012 | People | High turnover in engineering team | 4 | 3 | 12 | Retention programme with quarterly stay interviews and market-rate salary benchmarking | Head of Engineering | Mitigating | 2026-01-30 | 2026-04-30
RSK-013 | Data Privacy | Cross-border data transfer non-compliance | 2 | 5 | 10 | Data transfer impact assessments and Standard Contractual Clauses for all transfers | Data Protection Officer | Active | 2026-03-05 | 2026-06-05
RSK-014 | Operational | Legacy system failure causing service disruption | 3 | 3 | 9 | Phased migration plan with parallel running and automated failover | CTO | Mitigating | 2026-02-25 | 2026-05-25
RSK-015 | Compliance | Failure to maintain ISO 27001 certification | 2 | 4 | 8 | Internal audit programme with quarterly reviews and pre-certification gap analysis | Quality Manager | Active | 2026-01-05 | 2026-04-05